## web-case-list
# | Action | Expected Output | Platform | Smoke Test | Test Cycle - V2 | Executed By | Actual Output
REMN
1 | Verifying Filter dropdown button | Filter dropdown button will work properly | web |  | Passed | Umme Maria | found as per expectation
2 | Verifying each field without given data | will Show mandatory fields are required | web |  | Passed | Umme Maria | found as per expectation
3 | Verifying with mandatory fields | should be found all data | web |  | Failed | Umme Maria | not found as per expectation(Missing Graph Data)
4 | Verifying division field with specific data | Should be show valid data each field | web |  | Passed | Umme Maria | found as per expectation
5 | Verifying district field with specific data | Should be show valid data each field | web |  | Passed | Umme Maria | found as per expectation
6 | Verifying Upazila field with specific data | Should be show valid data each field | web |  | Passed | Umme Maria | found as per expectation
7 | Verifying Union field with specific data | Should be show valid data each field | web |  | Passed | Umme Maria | found as per expectation
8 | Verifying Period field after clear | Should be show all data | web |  | Failed | Umme Maria | Missing graph data
9 | Verifying Search button | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
10 | Verifying Total registered population value after create user using Smart Health BD app | Should be show accurate value | web |  | Failed | Umme Maria | not found as per expectation
11 | Verifying pregnant women registered value after registered pregnant women using Smart Health BD app | Should be show accurate value | web |  | Passed | Umme Maria | found as per expectation
12 | Verifying percentage of pregnant women registered value | Should be show accurate value | web |  | Failed | Umme Maria | not found as per expectation
13 | Verifying pregnant women registered graph value (Month Line data) | Should be show accurate value(month line data) | web |  | Failed | Umme Maria | not found as per expectation
14 | Verifying percentage of pregnant women registered graph value (Month Line data) | Should be show accurate value(month line data) | web |  | Failed | Umme Maria | not found as per expectation
15 | Verifying pregnant women registration graph value | Should be show accurate value | web |  | Passed | Umme Maria | found as per expectation
16 | Verifying percentage of pregnant women registration graph value | Should be show accurate value | web |  | Failed | Umme Maria | not found as per expectation
17 | Verifying percentage of pregnant women registered value using specific division | Should be show accurate value | web |  | Failed | Umme Maria | not found any data in graph
18 | Verifying Estimate Pregnant women value using select all division | Should be show accurate value | web |  | Failed | Umme Maria | Found dummy data
19 | Verifying Estimate Pregnant women value using select all division and all month | Should be show accurate value | web |  | Failed | Umme Maria | Found dummy data
20 | Verifying total pregnant women table's data each month | Should be found valid data each field | web |  | Failed | Umme Maria | not found as per expectation
21 | Verifying percentage of pregnant women registered table's data each month | Should be found valid data each field | web |  | Failed | Umme Maria | not found as per expectation
22 | Verifying download Excel button | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
23 | Verifying Pregnant women register's Burger icon | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
24 | Verifying Pregnant women register's Burger icon's download SVG | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
25 | Verifying Pregnant women register's Burger icon's download PNG | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
26 | Verifying Pregnant women register's Burger icon's download CSV | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
27 | Verifying percentage of Pregnant women register's Burger icon's download PNG | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
28 | Verifying percentage of Pregnant women register's Burger icon's download SVG | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
29 | Verifying percentage of Pregnant women register's Burger icon's download CSV | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
30 | Verifying percentage of Pregnant women registration status's Burger icon's download CSV | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
31 | Verifying percentage of Pregnant women registration status's Burger icon's download PNG | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
32 | Verifying percentage of Pregnant women registration status's Burger icon's download SVG | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
33 | Verifying Pregnant women registration status's Burger icon's download SVG | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
34 | Verifying Pregnant women registration status's Burger icon's download PNG | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
35 | Verifying Pregnant women registration status's Burger icon's download CSV | Should be work properly | web |  | Passed | Umme Maria | found as per expectation
Newborn and child
Newborn
36 | Verify Estimated pregnant women card | This is a static number which should align with recorded location data (refer from excel) | web | TRUE | Passed | Umme Maria | The estimated value is accurate
37 | Verify estimated birth card | This is a static number which should align with recorded location data (refer from excel) | web | TRUE | Passed | Umme Maria | The estimated value is accurate
38 | Verify total registered population card updates | If members are registered from app, then registered population number increases | web | TRUE | Passed | Umme Maria | The total population regsitered updates accordingly
39 | Verify number of newborn registered card updates | If a pregnant woman delivers a newborn or if a newborn is registered, then newborn registered should update | web | TRUE | Failed | Umme Maria | Newborn registered card does not update
40 | Filter newborn | User can filter all newborn graphs by period, months, locality. Locality are of 3 types (District, city coropration, Municipality). The branches are as follows district(division, disitrict, upazila, union, ward), CC (CC, zone, ward), Municipality (district, municipality, ward) | web | TRUE | Passed | Umme Maria | User can filter for specific locality using the heirarchies of location
41 | Mandatory Filter Validation | Period, months and locality must be selected for filter. After selecting localities the following parameters will be mandatory City Corporation - "CIty Corporation" District - "Division" Municipality - "District" | web | TRUE | Passed | Umme Maria | The mandatory field validation
42 | Verify Location hierarchy functionality | Location hierarchy will work properly, lower-level fields should appear on the selection on of higher-level fields | web | FALSE | Passed | Umme Maria | Location hierarchy works properly, lower-level fields appear on the selection on of higher-level fields
43 | Verify Dynamic Refreshment on Location Hierarchy | The options in the lower-level dropdowns should be refreshed dynamically based on the new selection in the higher-level dropdowns. | web | FALSE | Failed | Umme Maria | The options in the lower-level dropdowns don't refresh dynamically based on the new selection in the higher-level dropdowns.
44 | Validate form branching for locality field | filter form will populate with fields that are applicable for selected locality field | web | TRUE | Passed | Umme Maria | branching is okay
45 | Verify Newborn registration status graph | graph shows static value for estimated births. Values will update for number of newborn registered, precentage of newborn registered | web | TRUE | Failed | Umme Maria | This graph does not update
46 | Verfiy No of newborn with category weight graph | The pie chart should update for the following cateogories "Weight - >4500 gm", "Weight - 2500-4500 gm", "Weight -2000-2500 gm", "Weight - 1500-2000 gm", "Weight - 1000-1500 gm", "Weight - <1000gm" | web | TRUE | Failed | Umme Maria | This graph is not visible in the page
47 | Verify percentage of low brith weight baby graph | The percentage of low birth weight baby will calculate according to following population Calculation: (Count of Total child whose weight<2500 gm/Total No. of live birth)*100 | web | TRUE | Failed | Umme Maria | This graph does not update
48 | Verify Number of live births and still births graph | The number of live births or still birth will filter according to the newborn recorded from app as live or still birth birth. For still birth there is also count of total number of still birth fresh and macerated. Total delivery number will also be visible | web | TRUE | Failed | Umme Maria | The number of still births, still births(fresh), still births(macerated) does not update
49 | verify percentage of still birth graph | The percentage of still birth graph will update accroding to the following calculation- Calculation Logic: (Count of Still birth/ Count of total birth(Still +Live))*100 | web | TRUE | Failed | Umme Maria | This graph does not update
50 | verify percentage of pre-term baby graph | The percentage of pre-term baby will update according to the following calculation - Calculation Logic: (Total Pre-Term Baby/Total Live Birth)*100 | web | TRUE | Failed | Umme Maria | This graph does not update
51 | Verify number of newborn with any danger sign graph | The newborn registered and if in pnc followup shows any danger sign, then this number updates | web | TRUE | Failed | Umme Maria | This graph does not update
52 | Verify no of visible birth defect graph | newborn registered with visible birth defect will update the graph | web | TRUE | Failed | Umme Maria | This graph does not update
53 | Verify user can open and collapse filter section | User should be able to open and collapse filter section | web | TRUE | Passed | Umme Maria | User can open and close filter correctly
54 | Verify after filtering if user collapses filter section, the filter parameters should retain | If user selects parameters for filter and then closes it without leaving the window. Then opens the filter section again. Then it should retain the filter values. | web | TRUE | Failed | Umme Maria | Closing the filter removes all selected parameters
ENC | [5 empty] | Umme Maria
55 | Verify Estimated pregnant women card | This is a static number which should align with recorded location data (refer from excel) | web | TRUE | Passed | Umme Maria | The estimated value is accurate
56 | Verify estimated birth card | This is a static number which should align with recorded location data (refer from excel) | web | TRUE | Passed | Umme Maria | The estimated value is accurate
57 | Verify total registered population card updates | If members are registered from app, then registered population number increases | web | TRUE | Passed | Umme Maria | The total population regsitered updates accordingly
58 | Verify number of newborn registered card updates | If a pregnant woman delivers a newborn or if a newborn is registered, then newborn registered should update | web | TRUE | Failed | Umme Maria | Newborn registered card does not update
59 | Filter newborn | User can filter all newborn graphs by period, months, locality. Locality are of 3 types (District, city coropration, Municipality). The branches are as follows district(division, disitrict, upazila, union, ward), CC (CC, zone, ward), Municipality (district, municipality, ward) | web | TRUE | Passed | Umme Maria | User can filter for specific locality using the heirarchies of location
60 | Mandatory Filter Validation | Period, months and locality must be selected for filter. After selecting localities the following parameters will be mandatory City Corporation - "CIty Corporation" District - "Division" Municipality - "District" | web | TRUE | Passed | Umme Maria | The mandatory field validation
61 | Verify user can open and collapse filter section | User should be able to open and collapse filter section | web | TRUE | Passed | Umme Maria | User can open and close filter correctly
62 | Verify after filtering if user collapses filter section, the filter parameters should retain | If user selects parameters for filter and then closes it without leaving the window. Then opens the filter section again. Then it should retain the filter values. | web | TRUE | Failed | Umme Maria | Closing the filter removes all selected parameters
63 | Verify Location hierarchy functionality | Location hierarchy will work properly, lower-level fields should appear on the selection on of higher-level fields | web | FALSE | Passed | Umme Maria | Location hierarchy works properly, lower-level fields appear on the selection on of higher-level fields
64 | Verify Dynamic Refreshment on Location Hierarchy | The options in the lower-level dropdowns should be refreshed dynamically based on the new selection in the higher-level dropdowns. | web | FALSE | Failed | Umme Maria | The options in the lower-level dropdowns don't refresh dynamically based on the new selection in the higher-level dropdowns.
65 | Validate form branching for locality field | filter form will populate with fields that are applicable for selected locality field | web | TRUE | Passed | Umme Maria | branching is okay
66 | Verify no of child recieved ENC services graph | The services recieved for a new born should update the following points for this graph - Total Live Birth - Dried and wrapped immediately after birth - Skin to skin contact - Delayed cord cutting - Application of CHX - Breastfeed within 1 hour of delivery - Delayed bathing | web | TRUE | Failed | Umme Maria | No label updates besides total live birth
67 | Verify no of newborn with any danger sign graph | The count of newborns recorded with danger signs should be visible in the graph along with the total live birth count | web | TRUE | Passed | Umme Maria | This graph updates correctly
Death
68 | Verify Estimated pregnant women card | This is a static number which should align with recorded location data (refer from excel) | web | TRUE | Passed | Umme Maria | The estimated value is accurate
69 | Verify estimated birth card | This is a static number which should align with recorded location data (refer from excel) | web | TRUE | Passed | Umme Maria | The estimated value is accurate
70 | Verify number of newborn registered card updates | If a pregnant woman delivers a newborn or if a newborn is registered, then newborn registered should update | web | TRUE | Failed | Umme Maria | Newborn registered card does not update
71 | Verify number of neonatal deaths card | Newborns categorized as dead during delivery or children within 28 days of their dob | web | TRUE | Failed | Umme Maria | The card shows an incorrect count of death
72 | Filter newborn | User can filter all newborn graphs by period, months, locality. Locality are of 3 types (District, city coropration, Municipality). The branches are as follows district(division, disitrict, upazila, union, ward), CC (CC, zone, ward), Municipality (district, municipality, ward) | web | TRUE | Passed | Umme Maria | User can filter for specific locality using the heirarchies of location
73 | Mandatory Filter Validation | Period, months and locality must be selected for filter. After selecting localities the following parameters will be mandatory City Corporation - "CIty Corporation" District - "Division" Municipality - "District" | web | TRUE | Passed | Umme Maria | The mandatory field validation
74 | Verify user can open and collapse filter section | User should be able to open and collapse filter section | web | TRUE | Passed | Umme Maria | User can open and close filter correctly
75 | Verify after filtering if user collapses filter section, the filter parameters should retain | If user selects parameters for filter and then closes it without leaving the window. Then opens the filter section again. Then it should retain the filter values. | web | TRUE | Failed | Umme Maria | Closing the filter removes all selected parameters
76 | Verify Location hierarchy functionality | Location hierarchy will work properly, lower-level fields should appear on the selection on of higher-level fields | web | FALSE | Passed | Umme Maria | Location hierarchy works properly, lower-level fields appear on the selection on of higher-level fields
77 | Verify Dynamic Refreshment on Location Hierarchy | The options in the lower-level dropdowns should be refreshed dynamically based on the new selection in the higher-level dropdowns. | web | FALSE | Failed | Umme Maria | The options in the lower-level dropdowns don't refresh dynamically based on the new selection in the higher-level dropdowns.
78 | Validate form branching for locality field | filter form will populate with fields that are applicable for selected locality field | web | TRUE | Passed | Umme Maria | branching is okay
79 | Verify the graph for No of Neonatal death | The graph for neonatal death should update the following data points 1. Total live birth 2. No of Neonatal Death 3. Percentage of neonatal death | web | TRUE | Failed | Umme Maria | The graph shows incorrect percentage
80 | Verify No of Neonatal death by place graph | The graph for no of neonatal death should update the following data points - Medical College Hospital/Specialized Hospital - District Hospital - Upazila Health Complex - MCWC - UH&FWC/USC - Community Clinic - Private Hospital - NGO Clinic - Tea Garden Facility - Home - Other | web | TRUE | Failed | Umme Maria | The graph does not update for the following locations > - Medical College Hospital/Specialized Hospital - UH&FWC/USC - Community Clinic - Private Hospital - NGO Clinic - Tea Garden Facility - Home - Other
PNC
81 | Verify Estimated pregnant women card | This is a static number which should align with recorded location data (refer from excel) | web | TRUE | Passed | Umme Maria | The estimated value is accurate
82 | Verify estimated birth card | This is a static number which should align with recorded location data (refer from excel) | web | TRUE | Passed | Umme Maria | The estimated value is accurate
83 | Verify total registered population card updates | If members are registered from app, then registered population number increases | web | TRUE | Passed | Umme Maria | The total population regsitered updates accordingly
84 | Verify number of newborn registered card updates | If a pregnant woman delivers a newborn or if a newborn is registered, then newborn registered should update | web | TRUE | Failed | Umme Maria | Newborn registered card does not update
85 | Filter newborn | User can filter all newborn graphs by period, months, locality. Locality are of 3 types (District, city coropration, Municipality). The branches are as follows district(division, disitrict, upazila, union, ward), CC (CC, zone, ward), Municipality (district, municipality, ward) | web | TRUE | Passed | Umme Maria | User can filter for specific locality using the heirarchies of location
86 | Mandatory Filter Validation | Period, months and locality must be selected for filter. After selecting localities the following parameters will be mandatory City Corporation - "CIty Corporation" District - "Division" Municipality - "District" | web | TRUE | Passed | Umme Maria | The mandatory field validation
87 | Verify user can open and collapse filter section | User should be able to open and collapse filter section | web | TRUE | Passed | Umme Maria | User can open and close filter correctly
88 | Verify after filtering if user collapses filter section, the filter parameters should retain | If user selects parameters for filter and then closes it without leaving the window. Then opens the filter section again. Then it should retain the filter values. | web | TRUE | Failed | Umme Maria | Closing the filter removes all selected parameters
89 | Verify Location hierarchy functionality | Location hierarchy will work properly, lower-level fields should appear on the selection on of higher-level fields | web | FALSE | Passed | Umme Maria | Location hierarchy works properly, lower-level fields appear on the selection on of higher-level fields
90 | Verify Dynamic Refreshment on Location Hierarchy | The options in the lower-level dropdowns should be refreshed dynamically based on the new selection in the higher-level dropdowns. | web | FALSE | Failed | Umme Maria | The options in the lower-level dropdowns don't refresh dynamically based on the new selection in the higher-level dropdowns.
91 | Validate form branching for locality field | filter form will populate with fields that are applicable for selected locality field | web | TRUE | Passed | Umme Maria | branching is okay
92 | Verify No of child Received PNC Services graph | The child recieving PNC services will update the graph for the following data points - Total Delivery Registered - PNC-1 - PNC-2 - PNC-3 - PNC-4 | web | TRUE | Failed | Umme Maria | PNC services update when newborn is registered
ECCD
93 | Verify the number of children screened card | If children of ages between 2 months to 36 months complete ECCD services, then this number should update | web | TRUE | Passed | Umme Maria | Taking ECCD services updates the number of children screened card
94 | Verify the number of children identified card |  | web | TRUE | N/A | Umme Maria
95 | Verify the number of children identified and referred card | If children of ages between 2 to 36 months complete ECCD services and if they refer, then this number should update | web | TRUE | Passed | Umme Maria | The card updates accordingly
96 | Verify the number of children identified and not referred card | If children of ages between 2 to 36 months complete ECCD services and if they do not refer, then this number should update | web | TRUE | Passed | Umme Maria | The card updates accordingly
97 | Filter newborn | User can filter all newborn graphs by period, months, locality. Locality are of 3 types (District, city coropration, Municipality). The branches are as follows district(division, disitrict, upazila, union, ward), CC (CC, zone, ward), Municipality (district, municipality, ward) | web | TRUE | Passed | Umme Maria | User can filter for specific locality using the heirarchies of location
98 | Mandatory Filter Validation | Period, months and locality must be selected for filter. After selecting localities the following parameters will be mandatory City Corporation - "CIty Corporation" District - "Division" Municipality - "District" | web | TRUE | Passed | Umme Maria | The mandatory field validation
99 | Verify Location hierarchy functionality | Location hierarchy will work properly, lower-level fields should appear on the selection on of higher-level fields | web | FALSE | Passed | Umme Maria | Location hierarchy works properly, lower-level fields appear on the selection on of higher-level fields
100 | Verify Dynamic Refreshment on Location Hierarchy | The options in the lower-level dropdowns should be refreshed dynamically based on the new selection in the higher-level dropdowns. | web | FALSE | Failed | Umme Maria | The options in the lower-level dropdowns don't refresh dynamically based on the new selection in the higher-level dropdowns.
101 | Validate form branching for locality field | filter form will populate with fields that are applicable for selected locality field | web | TRUE | Passed | Umme Maria | branching is okay
102 | Verify user can open and collapse filter section | User should be able to open and collapse filter section | web | TRUE | Passed | Umme Maria | User can open and close filter correctly
103 | Verify after filtering if user collapses filter section, the filter parameters should retain | If user selects parameters for filter and then closes it without leaving the window. Then opens the filter section again. Then it should retain the filter values. | web | TRUE | Failed | Umme Maria | Closing the filter removes all selected parameters
104 | Verify ECCD Services statistics graph | Children of all ages within range of 2 months to 36 months will be included in this graph with the following data points -Number of Children Screened -Number of children identified on potential development delay -Number of children identified and referred -Number of children identified but not referred | web | TRUE | Passed | Umme Maria | All graph data points update accordingly
105 | Verify ECCD services statistics (2-3) months graph | Children of ages between 2 to 3 months will be included in this graph with the following data points -Number of Children Screened -Number of children identified on potential development delay -Number of children identified and referred -Number of children identified but not referred | web | TRUE | Passed | Umme Maria | All graph data points update accordingly
106 | Verify ECCD services statistics (4-6) months graph | Children of ages between 4 to 6 months will be included in this graph with the following data points -Number of Children Screened -Number of children identified on potential development delay -Number of children identified and referred -Number of children identified but not referred | web | TRUE | Passed | Umme Maria | All graph data points update accordingly
107 | Verify ECCD services statistics (7-9) months graph | Children of ages between 7 to 9 months will be included in this graph with the following data points -Number of Children Screened -Number of children identified on potential development delay -Number of children identified and referred -Number of children identified but not referred | web | TRUE | Passed | Umme Maria | All graph data points update accordingly
108 | Verify ECCD services statistics (10-17) months graph | Children of ages between 10 to 17 months will be included in this graph with the following data points -Number of Children Screened -Number of children identified on potential development delay -Number of children identified and referred -Number of children identified but not referred | web | TRUE | Failed | Umme Maria | Graph does not update at all
109 | Verify ECCD services statistics (18-23) months graph | Children of ages between 18 to 23 months will be included in this graph with the following data points -Number of Children Screened -Number of children identified on potential development delay -Number of children identified and referred -Number of children identified but not referred | web | TRUE | Passed | Umme Maria | All graph data points update accordingly
110 | Verify ECCD services statistics (36) months graph | Children of age of 36 months will be included in this graph with the following data points -Number of Children Screened -Number of children identified on potential development delay -Number of children identified and referred -Number of children identified but not referred | web | TRUE | Passed | Umme Maria | All graph data points update accordingly
Maternal > Register
111 | verify maternal > register default view | All cards and chart will display accurate data for the current year by default in national level | web | FALSE | Failed | Tamanna Molla Tanni | chart doesn't show correct data
112 | Verify user can open and collapse filter section | User should be able to open and collapse filter section | web | TRUE | Passed | Tamanna Molla Tanni | User can open and close filter correctly
113 | verify fiter fields mandatory field validation | users won't able to filter the dashboard without selecting mandatory fields [refer form excel] | web | FALSE | Passed | Tamanna Molla Tanni | users can't filter the dashboard without selecting mandatory fields [refer form excel]
114 | Verify Location hierarchy functionality | Location hierarchy will work properly, lower-level fields should appear on the selection on of higher-level fields | Web | FALSE | Passed | Tamanna Molla Tanni | Location hierarchy works properly, lower-level fields appear on the selection on of higher-level fields
115 | Verify Dynamic Refreshment on Location Hierarchy | The options in the lower-level dropdowns should be refreshed dynamically based on the new selection in the higher-level dropdowns. | Web | FALSE | Failed | Tamanna Molla Tanni | The options in the lower-level dropdowns don't refresh dynamically based on the new selection in the higher-level dropdowns.
116 | Verify after filtering if user collapses filter section, the filter parameters should retain | If user selects parameters for filter and then closes it without leaving the window. Then opens the filter section again. Then it should retain the filter values. | web | FALSE | Failed | Tamanna Molla Tanni | Closing the filter removes all selected parameters
117 | Validate form branching for locality field | filter form will populate with fields that are applicable for selected locality field | web | TRUE | Passed | Tamanna Molla Tanni | branching is okay
118 | Verify Estimated pregnant women card | estimated pregnant women card will show correct data base on the selected filtering and match with provided target file (main.xlsx) | web | FALSE | Failed | Tamanna Molla Tanni | estimated pregnant weman card doesn't show correct data when selecting all lower level location fields
119 | Verify estimated birth card | estimated birth card will show correct data base on the selected filtering and match with provided target file (main.xlsx) | web | FALSE | Failed | Tamanna Molla Tanni | estimated birth card doesn't show correct data when selecting all lower level location fields
120 | Verify total registered population card updates | If members are registered from app, then registered population number increases | web | FALSE | Passed | Tamanna Molla Tanni | The total population regsitered updates accordingly
121 | Verify Pregnant Women Registered card updates | If a pregnant woman is registered, then Pregnant Women Registered should update | web | FALSE | Failed | Tamanna Molla Tanni | Pregnant Women Registered registered card does not update
122 | Verify Percentage of Pregnant Women Registered card updates | Percentage of Pregnant Women Registered will appear correctly based on the selected filter | web | FALSE | Failed | Tamanna Molla Tanni | Percentage of Pregnant Women Registered doesn't show correctly
123 | verify Pregnant Women Registration Status graph | Estimated pregnant women, Pregnant Women Registered, Percentage of Pregnant Women Registered appears in the line chart correctly according to the selected filter | web | FALSE | Failed | Tamanna Molla Tanni | This graph show correct data for any legends
Maternal > ANC
124 | verify maternal > ANC default view | All cards and chart will display accurate data for the current year by default in national level | web | FALSE | Failed | Tamanna Molla Tanni | chart doesn't show correct data
125 | Verify user can open and collapse filter section | User should be able to open and collapse filter section | web | TRUE | Passed | Tamanna Molla Tanni | User can open and close filter correctly
126 | verify fiter fields mandatory field validation | users won't able to filter the dashboard without selecting mandatory fields [refer form excel] | web | FALSE | Passed | Tamanna Molla Tanni | users can't filter the dashboard without selecting mandatory fields [refer form excel]
127 | Verify Location hierarchy functionality | Location hierarchy will work properly, lower-level fields should appear on the selection on of higher-level fields | Web | FALSE | Passed | Tamanna Molla Tanni | Location hierarchy works properly, lower-level fields appear on the selection on of higher-level fields
128 | Verify Dynamic Refreshment on Location Hierarchy | The options in the lower-level dropdowns should be refreshed dynamically based on the new selection in the higher-level dropdowns. | Web | FALSE | Failed | Tamanna Molla Tanni | The options in the lower-level dropdowns don't refresh dynamically based on the new selection in the higher-level dropdowns.
129 | Verify after filtering if user collapses filter section, the filter parameters should retain | If user selects parameters for filter and then closes it without leaving the window. Then opens the filter section again. Then it should retain the filter values. | web | FALSE | Failed | Tamanna Molla Tanni | Closing the filter removes all selected parameters
130 | Validate form branching for locality field | filter form will populate with fields that are applicable for selected locality field | web | TRUE | Passed | Tamanna Molla Tanni | branching is okay
131 | Verify Estimated pregnant women card | estimated pregnant women card will show correct data base on the selected filtering and match with provided target file (main.xlsx) | web | FALSE | Failed | Tamanna Molla Tanni | estimated pregnant weman card doesn't show correct data when selecting all lower level location fields
132 | Verify estimated birth card | estimated birth card will show correct data base on the selected filtering and match with provided target file (main.xlsx) | web | FALSE | Failed | Tamanna Molla Tanni | estimated birth card doesn't show correct data when selecting all lower level location fields
133 | Verify Total Registered Population card updates | If members are registered from app, then registered population number increases | web | FALSE | Passed | Tamanna Molla Tanni | The total population regsitered updates accordingly
134 | Verify Total Pregnant Women Registered card updates | If a pregnant woman is registered, then Pregnant Women registered card should update | web | FALSE | Failed | Tamanna Molla Tanni | Pregnant Women Registered card does not update
135 | Verify ANC1 card updates | ANC1 will update correctly based on the selected filter when a pregnent women gets her first anc | web | FALSE | Passed | Tamanna Molla Tanni | ANC1 updates correctly based on the selected filter when a pregnent women gets her first anc
136 | Verify ANC2 card updates | ANC2 will update correctly based on the selected filter when a pregnent women gets her second anc | web | FALSE | Passed | Tamanna Molla Tanni | ANC2 updates correctly based on the selected filter when a pregnent women gets her second anc
137 | Verify ANC4 card updates | ANC1 will update correctly based on the selected filter when a pregnent women gets her third anc | web | FALSE | Passed | Tamanna Molla Tanni | ANC3 updates correctly based on the selected filter when a pregnent women gets her third anc
138 | Verify ANC4 card updates | ANC4 will update correctly based on the selected filter when a pregnent women gets her 4th anc | web | FALSE | Passed | Tamanna Molla Tanni | ANC4 updates correctly based on the selected filter when a pregnent women gets her 4th anc
139 | Verify Number of pregnent women with danger signs card updates | If a pregnant woman is marked with denger sign in her any anc form, then Number of pregnent women with danger signs card should update | web | FALSE | Failed | Tamanna Molla Tanni | Number of pregnent women with danger signs card updates multiple time for same woman
140 | verify No. of ANC-1, ANC-2 , ANC-3, ANC-4 graph | No. of ANC-1, ANC-2 , ANC-3, ANC-4 appears in the line chart correctly according to the selected filter | web | FALSE | Failed | Tamanna Molla Tanni | data entered for the previous month is displayed in the chart for the current month
141 | verify Percentage of ANC-1, ANC-2, ANC-3, ANC-4 graph | Percentage of ANC-1, ANC-2, ANC-3, ANC-4 appears in the line chart correctly according to the selected filter | web | FALSE | Not Tested | Tamanna Molla Tanni | couldn't test because of high estimated value
142 | verify ANC Service by Providers pie chart | ANC Service by Providers appears in current percentage in the pie chart correctly according to the selected filter | web | FALSE | Failed | Tamanna Molla Tanni | wrong percentage shows
143 | verify No. of Pregnant Women With Any Danger Sign graph | No. of Pregnant Women With Any Danger Sign appears in the line chart correctly according to the selected filter | web | FALSE | Failed | Tamanna Molla Tanni | No. of Pregnant Women With Any Danger Sign updates multiple times for the same woman getting multiple anc with danger sign
Maternal > Delivery
144 | Verify Default View for Delivery Dashboard | Delivery Dashboard will display accurate data for the current year at the national level by default. | web | FALSE | Failed | Umme Maria | chart doesn't show correct data
145 | Verify User Can Open and Collapse Filter Section | User should be able to open and collapse the filter section. | web | TRUE | Passed | Umme Maria | User can open and close filter correctly
146 | Verify Filter Fields Mandatory Field Validation | Users won't be able to filter the dashboard without selecting mandatory fields [refer to form Excel]. | web | FALSE | Passed | Umme Maria | users can't filter the dashboard without selecting mandatory fields [refer form excel]
147 | Verify Location Hierarchy Functionality | Location hierarchy will work properly, with lower-level fields appearing after the selection of higher-level fields. | Web | FALSE | Passed | Umme Maria | Location hierarchy works properly, lower-level fields appear on the selection on of higher-level fields
148 | Verify Dynamic Refreshment of Location Hierarchy | Lower-level dropdowns will refresh dynamically based on the new selection in higher-level dropdowns. | Web | FALSE | Failed | Umme Maria | The options in the lower-level dropdowns don't refresh dynamically based on the new selection in the higher-level dropdowns.
149 | Verify Filtering Parameters Retain on Collapse of Filter Section | If a user selects filter parameters and collapses the filter section without leaving the page, the parameters should be retained when reopened. | web | FALSE | Failed | Umme Maria | Closing the filter removes all selected parameters
150 | Validate form branching for locality field | filter form will populate with fields that are applicable for selected locality field | web | TRUE | Passed | Umme Maria | branching is okay
151 | Verify Estimated Pregnant Women Card | Estimated Pregnant Women card will show correct data based on the selected filtering and match the target file (main.xlsx). | web | FALSE | Failed | Umme Maria | estimated pregnant weman card doesn't show correct data when selecting all lower level location fields
152 | Verify Estimated Birth Card | Estimated Birth card will show correct data based on the selected filtering and match the target file (main.xlsx). | web | FALSE | Failed | Umme Maria | estimated birth card doesn't show correct data when selecting all lower level location fields
153 | Verify Total Delivery Card | Total Delivery card will show correct data based on the selected filtering and match the registered deliveries from the app. | web | FALSE | Failed | Umme Maria | Total Delivery card doesn't show correct data
154 | Verify Maternal Death Card | Maternal Death card will display the number of maternal deaths based on the selected filtering and match the provided target file (main.xlsx). | web | FALSE | Not Tested | Umme Maria | Maternal Death card doesnot update with relevent data submission from the app
155 | Verify Maternal Death Percentage Card (in 1000) | Maternal Death Percentage card will calculate and display the correct percentage per 1000 deliveries. | web | FALSE | Not Tested | Umme Maria | Maternal Death Percentage card doesnot update with relevent data submission from the app
156 | Verify Delivery Statistics Line Chart | Delivery Statistics line chart will correctly display estimated deliveries, total deliveries registered, and maternal deaths based on the selected filter. | web | FALSE | Failed | Umme Maria | data entered for the previous month is displayed in the chart for the current month
157 | Verify Total Delivery by Place of Delivery Line Chart | Total Delivery by Place of Delivery line chart will accurately show the places where the deliveries occurred (e.g., hospital, home, etc.) based on the selected filter. | web | FALSE | Not Tested | Umme Maria | Total Delivery by Place of Delivery chart doesnot update with relevent data submission from the app
158 | Verify Institutional Delivery Rate Pie Chart | Institutional Delivery Rate pie chart will show the correct percentage of deliveries that occurred in institutions based on the selected filter. | web | FALSE | Not Tested | Umme Maria | Institutional Delivery Rate chart doesnot update with relevent data submission from the app
159 | Verify Delivery Conducted by Providers Pie Chart | Delivery Conducted by Providers pie chart will display the current percentage of deliveries conducted by different providers based on the selected filter. | web | FALSE | Passed | Umme Maria | Delivery Conducted by Providers pie chart displays the current percentage of deliveries conducted by different providers based on the selected filter.
160 | Verify Mode of Delivery Pie Chart | Mode of Delivery pie chart will show the percentage breakdown of different delivery methods (e.g., C-section, normal, etc.) based on the selected filter. | web | FALSE | Failed | Umme Maria | Incorrect data is shown
161 | Verify Number of Live Births & Stillbirths Line Chart | Number of Live Births & Stillbirths line chart will correctly display data for live births and stillbirths according to the selected filter. | web | FALSE | Failed | Umme Maria | Incorrect data is shown
162 | Verify Complication Occurred and Type of Complication Bar Chart | Complication Occurred and Type of Complication bar chart will show the correct number of complications and types based on the selected filter. | web | FALSE | Not Tested | Umme Maria | Complication Occurred and Type of Complication chart doesnot update with relevent data submission from the app
163 | Verify Age of Death by Age Group Pie Chart | Age of Death by Age Group pie chart will correctly display the breakdown of maternal deaths by age group according to the selected filter. | web | FALSE | Not Tested | Umme Maria | Age of Death by Age Group chart doesnot update with relevent data submission from the app
164 | Verify Number of Deaths With Cause (According to Consultant with ICD Code) Pie Chart | Number of Deaths With Cause (According to Consultant with ICD Code) pie chart will show the correct cause of death and ICD code classification based on the selected filter. | web | FALSE | Not Tested | Umme Maria | Number of Deaths With Cause (According to Consultant with ICD Code) chart doesnot update with relevent data submission from the app
Maternal > PNC
165 | Verify Default View for PNC Dashboard | PNC Dashboard will display accurate data for the current year at the national level by default. | web | FALSE | Failed | Tamanna Molla Tanni | chart doesn't show correct data
166 | Verify User Can Open and Collapse Filter Section | User should be able to open and collapse the filter section. | web | TRUE | Passed | Tamanna Molla Tanni | User can open and close filter correctly
167 | Verify Filter Fields Mandatory Field Validation | Users won't be able to filter the dashboard without selecting mandatory fields [refer to form Excel]. | web | FALSE | Passed | Tamanna Molla Tanni | users can't filter the dashboard without selecting mandatory fields [refer form excel]
168 | Verify Location Hierarchy Functionality | Location hierarchy will work properly, with lower-level fields appearing after the selection of higher-level fields. | Web | FALSE | Passed | Tamanna Molla Tanni | Location hierarchy works properly, lower-level fields appear on the selection on of higher-level fields
169 | Verify Dynamic Refreshment of Location Hierarchy | Lower-level dropdowns will refresh dynamically based on the new selection in higher-level dropdowns. | Web | FALSE | Failed | Tamanna Molla Tanni | The options in the lower-level dropdowns don't refresh dynamically based on the new selection in the higher-level dropdowns.
170 | Verify Filtering Parameters Retain on Collapse of Filter Section | If a user selects filter parameters and collapses the filter section without leaving the page, the parameters should be retained when reopened. | web | FALSE | Failed | Tamanna Molla Tanni | Closing the filter removes all selected parameters
171 | Validate form branching for locality field | filter form will populate with fields that are applicable for selected locality field | web | TRUE | Passed | Tamanna Molla Tanni | branching is okay
172 | Verify Estimated Pregnant Women Card | Estimated Pregnant Women card will show correct data based on the selected filtering and match the target file (main.xlsx). | web | TRUE | Failed | Tamanna Molla Tanni | estimated pregnant weman card doesn't show correct data when selecting all lower level location fields
173 | Verify Estimated Birth Card | Estimated Birth card will show correct data based on the selected filtering and match the target file (main.xlsx). | web | FALSE | Failed | Tamanna Molla Tanni | estimated birth card doesn't show correct data when selecting all lower level location fields
174 | Verify Total Registered Population Card | Total Registered Population card will show the accurate population count based on the selected filtering and match the registered population from the app. | web | FALSE | Passed | Tamanna Molla Tanni | The total population regsitered updates accordingly
175 | Verify Total Pregnant Women Registered Card | Total Pregnant Women Registered card will update correctly when a new pregnant woman is registered based on the selected filter. | web | FALSE | Failed | Tamanna Molla Tanni | Pregnant Women Registered card does not update
176 | Verify PNC-1 Card | PNC-1 card will update correctly based on the selected filter when a mother receives her first postnatal care service. | web | FALSE | Not Tested | Tamanna Molla Tanni | PNC-1 Card doesnot update with relevent data submission from the app
177 | Verify PNC-2 Card | PNC-2 card will update correctly based on the selected filter when a mother receives her second postnatal care service. | web | FALSE | Not Tested | Tamanna Molla Tanni | PNC-2 Card doesnot update with relevent data submission from the app
178 | Verify PNC-3 Card | PNC-3 card will update correctly based on the selected filter when a mother receives her third postnatal care service. | web | FALSE | Not Tested | Tamanna Molla Tanni | PNC-3 Card doesnot update with relevent data submission from the app
179 | Verify PNC-4 Card | PNC-4 card will update correctly based on the selected filter when a mother receives her fourth postnatal care service. | web | FALSE | Not Tested | Tamanna Molla Tanni | PNC-4 Card doesnot update with relevent data submission from the app
180 | Verify No. of Mother Received PNC Services Line Chart | No. of Mother Received PNC Services line chart will correctly display PNC1, PNC2, PNC3, and PNC4 counts according to the selected filter. | web | FALSE | Not Tested | Tamanna Molla Tanni | No. of Mother Received PNC Services Chart doesnot update with relevent data submission from the app
181 | Verify Percentage of Mothers Receiving PNC Services Line Chart | Percentage of Mothers Receiving PNC Services line chart will display the correct percentage of mothers receiving PNC services (PNC1, PNC2, PNC3, PNC4) based on the selected filter. | web | FALSE | Not Tested | Tamanna Molla Tanni | Percentage of Mothers Receiving PNC Services Chart doesnot update with relevent data submission from the app

## Report
Version | Blocked | Passed | Failed | Not Tested | N/A | Total
V1.0.1 | 0 | 93 | 73 | 14 | 1 | 181
v3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
v4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
v5
Total | #REF! | #REF! | #REF! | #REF! | #REF!