## Test Plan
Test Plan
mPower Social Enterprises Ltd.
Project |  | Prepared By |  | Date | Approved By
Unicef DGHS Community Health (HA Dashboard) JIRA version 2 |  | Umme Maria |  | 2024-08-20 | Mojammel Hossain
Sl. No. | Name of Feature |  |  | Time Required (hrs) | No. of Resource Allocated
1 | UI Testing |  |  | 8 | 1
2 | User Administration (Mobile User) |  |  | 8 | 1
3 | Manual data submission (Mobile app flow) |  |  | 24 | 1
4 | Bulk data enumeration in Burp Suite |  |  | 16 | 1
5 | Data Integrity for various Reports |  |  | 48 | 1
6 | Homepage Visualization |  |  | 8 | 1
7 | Test plan and environment setup |  |  | 8 | 1
|  |  | Hours for 1 tester | 120 | 15
|  |  | Test Plan for |  | 15 | days
~ Test cycle will start date >>> 20/08/2024 and end date >>> 10/09/2024. [August 26 (Monday) - Government Holiday(Janmashtami )]
~ This plan is only for the functional testing of the application. The time for regression cycle(s) will depend on the number of bugs and change requests yet to come. [Generally the time for regression testing = ½ the time for functional testing.]
~ The project lacks an appropriate mockup, including a missing mockup for the Dashboards. The available mockup only covers the homepage, which is outdated.
~ Bulk data will be submitted using Burp Suite in limited scope. Although submitting data by running a script through JMeter would be more appropriate, but that is outside scope due to time constraints and lack of api documentation
~ Citizen Corner and Tutorial sections are outside the scope of testing